## Conditions affect COTS dives
Date | Vessel | Region | Reef | Days lost | Reason | Dives impacted
2020-02-24 | Venus II | Northern | Batt 16-029 | 0.5 | Strong wind and swell conditions | 2
2020-02-25 | Venus II | Northern | Ribbon No3 | 0.5 | Strong wind and swell conditions | 2
2020-02-26 | Venus II | Northern | Ribbon No4 | 0.5 | Strong wind and swell conditions | 2
2020-03-07 | Hero | Northern | Moore 16-071 | 1 | Poor visibility | 4
2020-03-30 | Hero | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2020-03-30 | Venus II | Northern | Farquharson 17-063a | 1 | Strong wind and swell conditions | 4
2020-03-31 | Hero | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2020-03-31 | Tura | Northern | Farquharson 17-063a | 1 | Strong wind and swell conditions | 4
2020-03-31 | Venus II | Northern | Farquharson 17-063a | 1 | Strong wind and swell conditions | 4
2020-04-01 | Hero | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2020-04-01 | Venus II | Northern | Farquharson 17-063a | 1 | Strong wind and swell conditions | 4
2020-04-02 | Hero | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2020-04-02 | Venus II | Northern | Farquharson 17-063a | 1 | Strong wind and swell conditions | 4
2020-04-03 | Hero | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2020-04-03 | Venus II | Northern | Farquharson 17-063a | 1 | Strong wind and swell conditions | 4
2020-04-04 | Venus II | Northern | Farquharson 17-063a | 1 | Strong wind and swell conditions | 4
2020-04-20 | Hero | Northern | Cairns Port | 1 | Mechanical issues | 4
2020-07-03 | Hero | Northern | Moore 16-071 | 1 | Strong wind and swell conditions | 4
2020-07-06 | Hero | Northern | Moore 16-071 | 1 | Strong wind and swell conditions | 4
2020-07-09 | Hero | Northern | Sudbury 17-001a | 1 | Strong wind and swell conditions | 4
2020-07-27 | Hero | Northern | Sudbury 17-001a | 1 | Strong wind and swell conditions | 4
2020-07-29 | Hero | Northern | Sudbury 17-001a | 1 | Strong wind and swell conditions | 4
2020-07-30 | Hero | Northern | Sudbury 17-001a | 1 | Strong wind and swell conditions | 4
2020-09-03 | Hero | Northern | Trunk 18-027 | 0.5 | Strong wind and swell conditions | 2
2020-09-15 | Hero | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2020-09-18 | Hero | Northern | Moore 16-071 | 0.5 | Strong wind and swell conditions | 2
2021-02-23 | Hero | Northern | Fitzroy Island | 0.25 | Tiger shark | 1
2021-07-07 | Venus II | Northern | Cairns Port | 1 | Mechanical issues | 4
2021-07-08 | Venus II | Northern | Cairns Port | 1 | Mechanical issues | 4
2021-07-20 | Tura | Northern | Cairns Port | 1 | Mechanical issues | 4
2021-08-05 | Tura | Central | Magnetic Island | 1 | Covid crew dropped off | 4
2021-08-07 | Hero | Northern | Return to Cairns port | 1 | Mechanical issues | 4
2021-08-08 | Hero | Northern | Return to Cairns port | 1 | Mechanical issues | 4
2021-08-09 | Hero | Northern | Return to Cairns port | 1 | Mechanical issues | 4
2021-08-10 | Hero | Northern | Return to Cairns port | 1 | Mechanical issues | 4
2021-08-11 | Hero | Northern | Return to Cairns port | 1 | Mechanical issues | 4
2021-08-12 | Tura | Central | Magnetic Island | 1 | Covid crew dropped off | 4
2021-08-17 | Venus II | Northern | Cairns Port | 1 | Mechanical issues | 4
2021-08-18 | Venus II | Northern | Cairns Port | 1 | Mechanical issues | 4
2021-08-19 | Venus II | Northern | Cairns Port | 1 | Mechanical issues | 4
2021-08-24 | Venus II | Northern | Cairns Port | 1 | Mechanical issues | 4
2021-08-25 | Venus II | Northern | Cairns Port | 1 | Mechanical issues | 4
2021-08-26 | Venus II | Northern | Cairns Port | 1 | Mechanical issues | 4
2021-09-07 | Hero | Central | Britomart | 1 | Strong wind and swell conditions | 4
2021-09-07 | Tura | Central | Walker | 1 | Strong wind and swell conditions | 4
2021-09-07 | Venus II | Northern | Elford 16-073 | 1 | Strong wind and swell conditions | 4
2021-09-08 | Hero | Northern | Eddy | 1 | Strong wind and swell conditions | 4
2021-09-08 | Tura | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2021-09-08 | Venus II | Northern | Elford 16-073 | 1 | Strong wind and swell conditions | 4
2021-09-22 | Tura | Northern | Round Russell | 1 | Strong wind and swell conditions | 4
2021-09-22 | Venus II | Northern | Elford 16-073 | 1 | Strong wind and swell conditions | 4
2021-11-16 | Hero | Northern | Batt 16-029 | 0.5 | Thunder and lightning storm | 2
2021-12-13 | Tura | Central | Bowden | 0.5 | Strong wind and swell conditions | 2
2022-01-10 | Venus II | Northern | Green Island | 1 | Strong wind and swell conditions | 4
2022-01-11 | Tura | Northern | Return to Cairns port | 1 | Covid presented, trip aborted | 4
2022-01-12 | Tura | Northern | Return to Cairns port | 1 | Covid presented, trip aborted | 4
2022-01-22 | Hero | Northern | Elford 16-073 | 1 | Strong wind and swell conditions | 4
2022-02-05 | Hero | Central | Trunk 18-027 | 1 | Strong wind and swell conditions | 4
2022-02-05 | Tura | Central | Davies | 1 | Strong wind and swell conditions | 4
2022-02-20 | Hero | Central | Pith 18-033 | 0.75 | Strong wind and swell conditions | 3
2022-03-03 | Hero | Central | Pith 18-033 | 0.5 | Strong wind and swell conditions | 2
2022-03-04 | Hero | Central | Trunk 18-027 | 0.5 | Strong wind and swell conditions | 2
2022-03-09 | Venus II | Northern | Fitzroy Island | 1 | Master Reef Guide Training | 4
2022-03-10 | Venus II | Northern | Fitzroy Island | 1 | Master Reef Guide Training | 4
2022-03-16 | Tura | Northern | Eddy | 1 | Strong wind and swell conditions | 4
2022-03-17 | Hero | Northern | Nathan | 0.25 | Irukandji sightings | 1
2022-03-18 | Hero | Central | Trunk 18-027 | 1 | Strong wind and swell conditions | 4
2022-03-18 | Venus II | Northern | Batt 16-029 | 1 | Strong wind and swell conditions | 4
2022-03-19 | Hero | Central | Trunk 18-027 | 1 | Strong wind and swell conditions | 4
2022-04-01 | Hero | Central | Trunk 18-027 | 0.5 | Strong wind and swell conditions | 2
2022-04-02 | Hero | Northern | Cairns Port | 1 | Flu like sympthoms crew | 4
2022-04-03 | Hero | Northern | Cairns Port | 1 | Flu like sympthoms crew | 4
2022-04-04 | Hero | Northern | Cairns Port | 1 | Flu like sympthoms crew | 4
2022-04-04 | Venus II | Northern | Return to Cairns port | 1 | Covid presented, trip aborted | 4
2022-04-05 | Hero | Northern | Cairns Port | 1 | Flu like sympthoms crew | 4
2022-04-05 | Venus II | Northern | Return to Cairns port | 1 | Covid presented, trip aborted | 4
2022-04-06 | Hero | Northern | Cairns Port | 1 | Flu like sympthoms crew | 4
2022-04-06 | Venus II | Northern | Return to Cairns port | 1 | Covid presented, trip aborted | 4
2022-04-07 | Hero | Northern | Cairns Port | 1 | Flu like sympthoms crew | 4
2022-04-07 | Venus II | Northern | Return to Cairns port | 1 | Covid presented, trip aborted | 4
2022-04-13 | Hero | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2022-04-13 | Tura | Northern | Cairns Port | 1 | Mechanical issues | 4
2022-04-14 | Hero | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2022-04-14 | Tura | Northern | Cairns Port | 1 | Mechanical issues | 4
2022-04-15 | Hero | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2022-04-15 | Tura | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2022-04-27 | Hero | Northern | Briggs | 1 | Strong wind and swell conditions | 4
2022-04-27 | Tura | Central | Davies | 1 | Strong wind and swell conditions | 4
2022-04-27 | Venus II | Northern | Arlington | 1 | Strong wind and swell conditions | 4
2022-04-29 | Hero | Northern | Moore 16-071 | 0.75 | Strong wind and swell conditions | 3
2022-04-29 | Tura | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2022-04-29 | Venus II | Northern | U/N 16-027 | 1 | Strong wind and swell conditions | 4
2022-05-03 | Tura | Northern | Cairns Port | 1 | Unwell crew members x4 | 4
2022-05-11 | Tura | Central | Kelso | 1 | Strong wind and swell conditions | 4
2022-05-12 | Tura | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2022-05-13 | Venus II | Northern | Lena 15-085 | 0.5 | Mechanical issues | 2
2022-05-17 | Venus II | Northern | Eyrie 14-118 | 0.5 | Responded to ship distress signal | 2
2022-05-19 | Venus II | Northern | Lena 15-085 | 0.5 | Strong wind and swell conditions | 2
2022-06-09 | Hero | Northern | Batt 16-029 | 1 | Strong wind and swell conditions | 4
2022-06-09 | Venus II | Northern | Lizard Island | 1 | Strong wind and swell conditions | 4
2022-06-10 | Hero | Northern | Batt 16-029 | 1 | Strong wind and swell conditions | 4
2022-06-10 | Venus II | Northern | Lizard Island | 1 | Strong wind and swell conditions | 4
2022-06-11 | Venus II | Northern | Lizard Island | 1 | Strong wind and swell conditions | 4
2022-06-12 | Venus II | Northern | Lizard Island | 1 | Strong wind and swell conditions | 4
2022-06-14 | Venus II | Northern | Cairns | 1 | Strong wind and swell conditions | 4
2022-06-22 | Tura | Central | Fore and Aft | 1 | Strong wind and swell conditions | 4
2022-06-22 | Venus II | Central | Magnetic Island | 1 | Drop off sick crew | 4
2022-06-23 | Hero | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2022-06-23 | Tura | Central | Fore and Aft | 1 | Strong wind and swell conditions | 4
2022-06-26 | Hero | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2022-06-26 | Tura | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2022-06-27 | Hero | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2022-06-27 | Tura | Central | Big Broadhurst No2 | 1 | Strong wind and swell conditions | 4
2022-06-27 | Venus II | Central | Davies | 1 | Strong wind and swell conditions | 4
2022-06-28 | Hero | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2022-06-28 | Tura | Central | Big Broadhurst No3 | 1 | Strong wind and swell conditions | 4
2022-06-28 | Venus II | Central | Britomart | 1 | Strong wind and swell conditions | 4
2022-06-29 | Capricorn Star | Northern | Batt 16-029 | 1 | Strong wind and swell conditions | 4
2022-06-29 | Hero | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2022-06-29 | Tura | Central | Big Broadhurst No4 | 1 | Strong wind and swell conditions | 4
2022-06-29 | Venus II | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2022-06-30 | Capricorn Star | Northern | Batt 16-029 | 0.5 | Strong wind and swell conditions | 2
2022-07-02 | Capricorn Star | Northern | Batt 16-029 | 1 | Strong wind and swell conditions | 4
2022-07-02 | Tura | Central | Fore and Aft | 1 | Strong wind and swell conditions | 4
2022-07-04 | Tura | Central | Fore and Aft | 1 | Strong wind and swell conditions | 4
2022-07-07 | Capricorn Star | Northern | Escape 15-094 | 0.25 | Strong wind and swell conditions | 1
2022-07-11 | Capricorn Star | Northern | Batt 16-029 | 1 | Strong wind and swell conditions | 4
2022-07-19 | Venus II | Northern | Cairns Port | 1 | Mechanical issues | 4
2022-07-20 | Capricorn Star | Northern | Eyrie 14-118 | 0.75 | Mechanical issues | 3
2022-07-24 | Venus II | Northern | Cairns Port | 1 | Covid presented, trip aborted | 4
2022-07-25 | Venus II | Northern | Cairns Port | 1 | Covid presented, trip aborted | 4
2022-07-26 | Venus II | Northern | Cairns Port | 1 | Covid presented, trip aborted | 4
2022-07-27 | Venus II | Northern | Cairns Port | 1 | Covid presented, trip aborted | 4
2022-07-28 | Capricorn Star | Northern | Cairns Port | 1 | Mechanical issues | 4
2022-07-28 | Venus II | Northern | Cairns Port | 1 | Covid presented, trip aborted | 4
2022-08-09 | Tura | Northern | Elford 16-073 | 1 | Strong wind and swell conditions | 4
2022-08-17 | Capricorn Star | Northern | Cairns Port | 1 | Electrical issues | 4
2022-08-24 | Hero | Northern | Elford 16-073 | 1 | Strong wind and swell conditions | 4
2022-08-24 | Tura | Northern | Wardle | 1 | Strong wind and swell conditions | 4
2022-08-31 | Hero | Central | Trunk | 1 | Strong wind and swell conditions | 4
2022-08-31 | Tura | Northern | Adelaide | 1 | Strong wind and swell conditions | 4
2022-10-01 | Tura | Central | Big Broadhurst No1 | 0.25 | Bull sharks large | 1
2022-11-01 | Tura | Central | Fore and Aft | 1 | Strong wind and swell conditions | 4
2022-11-02 | Capricorn Star | Northern | Batt 16-029 | 1 | Strong wind and swell conditions | 4
2022-11-02 | Tura | Northern | Normanby-Mabel | 1 | Strong wind and swell conditions | 4
2022-11-02 | Venus II | Northern | Batt 16-029 | 0.5 | Strong wind and swell conditions | 2
2022-11-03 | Capricorn Star | Northern | Eyrie 14-118 | 1 | Strong wind and swell conditions | 4
2022-11-04 | Capricorn Star | Northern | Eyrie 14-118 | 0.75 | Strong wind and swell conditions | 3
2022-11-05 | Capricorn Star | Northern | Eyrie 14-118 | 1 | Strong wind and swell conditions | 4
2022-11-06 | Capricorn Star | Northern | Lizard Island | 1 | Strong wind and swell conditions | 4
2022-11-10 | Hero | Northern | Cairns Port | 1 | Mechanical issues | 4
2022-11-14 | Venus II | Northern | Cooktown | 1 | Injured crew drop off | 4
2022-11-20 | Venus II | Northern | Cooktown | 1 | Crew drop off | 4
2022-11-29 | Hero | Northern | Cairns Port | 1 | Mechanical issues | 4
2022-11-30 | Hero | Northern | Cairns Port | 1 | Mechanical issues | 4
2022-12-01 | Hero | Northern | Cairns Port | 1 | Mechanical issues | 4
2022-12-02 | Hero | Northern | Cairns Port | 1 | Mechanical issues | 4
2022-12-03 | Hero | Northern | Cairns Port | 1 | Mechanical issues | 4
2022-12-04 | Hero | Northern | Cairns Port | 1 | Mechanical issues | 4
2022-12-05 | Hero | Northern | Cairns Port | 1 | Mechanical issues | 4
2022-12-07 | Venus II | Northern | Cairns Port | 1 | Covid presented, trip aborted | 4
2022-12-08 | Venus II | Northern | Cairns Port | 1 | Covid presented, trip aborted | 4
2023-01-05 | Capricorn Star | Northern | Linnet 14-126 | 0.5 | Strong wind and swell conditions | 2
2023-01-06 | Capricorn Star | Northern | Martin 14-123 | 0.5 | Strong wind and swell conditions | 2
2023-01-06 | Tura | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2023-01-06 | Tura | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2023-01-07 | Capricorn Star | Northern | Martin 14-123 | 0.25 | Bull sharks large | 1
2023-01-09 | Capricorn Star | Northern | Steam to Cooktown | 1 | Mechanical issues | 4
2023-01-12 | Capricorn Star | Northern | Rocky Islet 14-132a | 0.5 | Crocodile sighting | 2
2023-01-13 | Hero | Northern | Green Island | 0.5 | Irukandji sightings | 2
2023-01-13 | Tura | Central | Fore and Aft | 0.25 | Poor visibility | 1
2023-01-25 | Hero | Northern | Batt 16-029 | 0.75 | Irukandji sightings | 3
2023-01-25 | Venus II | Northern | Pickersgill 15-093 | 0.25 | Irukandji sightings | 1
2023-02-01 | Tura | Central | Big Broadhurst No2 | 0.025 | Poor visibility | 1
2023-02-16 | Hero | Northern | Batt 16-029 | 1 | Strong wind and swell conditions | 4
2023-02-16 | Venus II | Northern | Startle 15-028 | 1 | Strong wind and swell conditions | 4
2023-02-18 | Venus II | Northern | Martin 14-123 | 0.5 | Irukandji sightings | 2
2023-02-19 | Capricorn Star | Northern | Michaelmas 16-062 | 0.5 | Strong wind and swell conditions | 2
2023-02-22 | Venus II | Northern | Martin 14-123 | 1 | Irukandji sightings | 4
2023-02-23 | Capricorn Star | Northern | Green Island | 1 | Strong wind and swell conditions | 4
2023-02-25 | Capricorn Star | Northern | Martin 14-123 | 0.5 | Strong wind and swell conditions | 2
2023-02-27 | Capricorn Star | Northern | Michaelmas 16-062 | 1 | Strong wind and swell conditions | 4
2023-03-05 | Hero | Northern | Flynn 16-071 | 0.25 | Divers recalled due to tourism vessel on site | 1
2023-03-05 | Venus II | Northern | Cooktown | 1 | Mechanical issues | 4
2023-03-19 | Capricorn Star | Northern | Tongue 16-026 | 0.25 | Strong currents | 1
2023-03-19 | Hero | Northern | Gibson 17-017 | 1 | High swell and poor visibility | 4
2023-03-20 | Venus II | Northern | Evening 15-095 | 0.25 | Strong wind and swell conditions | 1
2023-03-21 | Hero | Northern | Sudbury 17-001a | 1 | Strong wind and swell conditions | 4
2023-03-21 | Tura | Central | Trunk | 1 | Strong wind and swell conditions | 4
2023-03-22 | Tura | Central | Otter | 1 | Strong wind and swell conditions | 4
2023-03-22 | Venus II | Northern | U/N 16-027 | 0.5 | Strong wind and swell conditions | 2
2023-04-19 | Tura | Central | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2023-04-20 | Hero | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2023-04-21 | Hero | Northern | Return to Cairns port | 1 | Strong wind and swell conditions | 4
2023-04-22 | Hero | Northern | Return to Cairns port | 1 | Strong wind and swell conditions | 4
2023-04-23 | Hero | Northern | Return to Cairns port | 1 | Strong wind and swell conditions | 4
2023-04-24 | Hero | Northern | Return to Cairns port | 1 | Strong wind and swell conditions | 4
2023-04-26 | Hero | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2023-04-26 | Tura | Central | Adelaide | 1 | Strong wind and swell conditions | 4
2023-04-26 | Venus II | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2023-04-27 | Tura | Central | Adelaide | 1 | Strong wind and swell conditions | 4
2023-04-27 | Venus II | Northern | Michaelmas 16-062 | 1 | Strong wind and swell conditions | 4
2023-04-28 | Venus II | Northern | Cairns | 1 | Strong wind and swell conditions | 4
2023-05-03 | Capricorn Star | Northern | Osterlund 15-078 | 1 | Strong wind and swell conditions | 4
2023-05-04 | Capricorn Star | Northern | Osterlund 15-078 | 1 | Strong wind and swell conditions | 4
2023-05-04 | Hero | Northern | Return to Cairns port | 1 | Strong wind and swell conditions | 4
2023-05-05 | Capricorn Star | Northern | Osterlund 15-078 | 1 | Strong wind and swell conditions | 4
2023-05-06 | Capricorn Star | Northern | Osterlund 15-078 | 1 | Strong wind and swell conditions | 4
2023-05-08 | Capricorn Star | Northern | Osterlund 15-078 | 1 | Strong wind and swell conditions | 4
2023-05-09 | Tura | Central | Port | 1 | Mechanical issues | 4
2023-05-10 | Venus II | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2023-05-12 | Tura | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2023-05-13 | Tura | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2023-05-13 | Venus II | Central | Trunk 18-027 | 1 | Strong wind and swell conditions | 4
2023-05-24 | Tura | Central | Adelaide | 1 | Strong wind and swell conditions | 4
2023-05-24 | Venus II | Northern | Sudbury 17-001a | 1 | Strong wind and swell conditions | 4
2023-05-25 | Venus II | Northern | Sudbury 17-001a | 1 | Strong wind and swell conditions | 4
2023-07-10 | Venus II | Northern | Rudder 16-023 | 1 | Strong wind and swell conditions | 4
2023-07-11 | Capricorn Star | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2023-07-13 | Capricorn Star | Central | Britomart | 1 | Strong wind and swell conditions | 4
2023-07-14 | Capricorn Star | Central | Beaver 17-051 | 1 | Strong wind and swell conditions | 4
2023-07-16 | Capricorn Star | Central | Nathan 17-035 | 1 | Strong wind and swell conditions | 4
2023-07-17 | Capricorn Star | Northern | Green Island | 1 | Strong wind and swell conditions | 4
2023-07-19 | Tura | Northern | Moore 16-071 | 1 | Strong wind and swell conditions | 4
2023-07-19 | Venus II | Northern | Moore 16-071 | 1 | Strong wind and swell conditions | 4
2023-07-24 | Tura | Central | Backnumbers | 1 | Strong wind and swell conditions | 4
2023-07-24 | Venus II | Northern | Green Island | 1 | Strong wind and swell conditions | 4
2023-07-25 | Venus II | Northern | Green Island | 1 | Strong wind and swell conditions | 4
2023-07-26 | Capricorn Star | Northern | Flynn 16-071 | 1 | Strong wind and swell conditions | 4
2023-07-26 | Tura | Northern | Sudbury 17-001a | 1 | Strong wind and swell conditions | 4
2023-07-26 | Venus II | Northern | Green Island | 1 | Strong wind and swell conditions | 4
2023-07-27 | Capricorn Star | Northern | Moore 16-071 | 1 | Strong wind and swell conditions | 4
2023-08-02 | Tura | Northern | Eddy | 1 | Strong wind and swell conditions | 4
2023-08-03 | Capricorn Star | Northern | Moore 16-071 | 1 | Strong wind and swell conditions | 4
2023-08-03 | Tura | Central | Fore and Aft | 1 | Strong wind and swell conditions | 4
2023-08-03 | Venus II | Northern | Batt 16-029 | 1 | Strong wind and swell conditions | 4
2023-08-04 | Capricorn Star | Northern | Moore 16-071 | 1 | Strong wind and swell conditions | 4
2023-08-04 | Tura | Central | Fore and Aft | 1 | Strong wind and swell conditions | 4
2023-08-04 | Venus II | Northern | Batt 16-029 | 1 | Strong wind and swell conditions | 4
2023-08-05 | Capricorn Star | Northern | Moore 16-071 | 1 | Strong wind and swell conditions | 4
2023-08-05 | Venus II | Northern | Batt 16-029 | 1 | Strong wind and swell conditions | 4
2023-08-06 | Capricorn Star | Northern | Moore 16-071 | 1 | Strong wind and swell conditions | 4
2023-08-06 | Tura | Central | Fore and Aft | 1 | Strong wind and swell conditions | 4
2023-08-06 | Venus II | Northern | Batt 16-029 | 1 | Strong wind and swell conditions | 4
2023-08-07 | Capricorn Star | Northern | Moore 16-071 | 1 | Strong wind and swell conditions | 4
2023-08-07 | Venus II | Northern | Batt 16-029 | 1 | Strong wind and swell conditions | 4
2023-08-19 | Tura | Central | Hopkinson | 1 | Strong wind and swell conditions | 4
2023-08-24 | Capricorn Star | Northern | Osterlund 15-078 | 1 | Strong wind and swell conditions | 4
2023-08-25 | Capricorn Star | Northern | Batt 16-029 | 1 | Strong wind and swell conditions | 4
2023-08-26 | Capricorn Star | Northern | Green Island | 1 | Strong wind and swell conditions | 4
2023-08-27 | Capricorn Star | Northern | Green Island | 1 | Strong wind and swell conditions | 4
2023-09-11 | Capricorn Star | Central | Hopkinson | 1 | Strong wind and swell conditions | 4
2023-09-12 | Capricorn Star | Central | Hopkinson | 1 | Strong wind and swell conditions | 4
2023-09-13 | Capricorn Star | Central | Hopkinson | 1 | Strong wind and swell conditions | 4
2023-09-13 | Venus II | Northern | Fitzroy Island | 1 | Strong wind and swell conditions | 4
2023-09-14 | Capricorn Star | Central | Hopkinson | 1 | Strong wind and swell conditions | 4
2023-09-15 | Capricorn Star | Central | Britomart | 1 | Strong wind and swell conditions | 4
2023-09-16 | Venus II | Northern | Moore 16-071 | 0.5 | Strong wind and swell conditions | 2
2023-09-19 | Venus II | Northern | Batt 16-029 | 0.5 | Strong wind and swell conditions | 2
2023-10-29 | Capricorn Star | Central | Yamacutta | 1 | Strong wind and swell conditions | 4
2023-10-29 | Venus II | Northern | Lizard Island | 0.5 | Strong wind and swell conditions | 2
2023-11-11 | Venus II | Northern | Lark 15-033 | 0.25 | Jelly fish in large abundance | 1
2023-12-09 | Capricorn Star | Northern | Return to Cairns port | 1 | Mechanical issues | 4
2023-12-09 | Tura | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-10 | Capricorn Star | Northern | Return to Cairns port | 1 | Mechanical issues | 4
2023-12-10 | Tura | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-10 | Venus II | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-11 | Capricorn Star | Northern | Return to Cairns port | 1 | Mechanical issues | 4
2023-12-11 | Tura | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-11 | Venus II | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-12 | Capricorn Star | Northern | Return to Cairns port | 1 | Mechanical issues | 4
2023-12-12 | Tura | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-12 | Venus II | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-13 | Capricorn Star | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-13 | Tura | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-13 | Venus II | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-14 | Capricorn Star | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-14 | Tura | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-14 | Venus II | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-15 | Capricorn Star | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-15 | Tura | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-15 | Venus II | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-16 | Capricorn Star | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-16 | Tura | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-16 | Venus II | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-17 | Capricorn Star | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-17 | Tura | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-17 | Venus II | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-18 | Capricorn Star | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-18 | Tura | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-18 | Venus II | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-19 | Capricorn Star | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2023-12-19 | Venus II | Northern | Return to Cairns port | 1 | Abort trip due to Cyclone Jasper | 4
2024-01-26 | Capricorn Star | Northern | Lark 15-033 | 1 | Strong wind and swell conditions | 4
2024-01-27 | Capricorn Star | Northern | Lark 15-033 | 1 | Strong wind and swell conditions | 4
2024-03-07 | Venus II | Northern | Rudder 16-023 | 1 | Strong wind and swell conditions | 4
2024-03-09 | Capricorn Star | Northern | Eyrie 14-118 | 1 | Strong wind and swell conditions | 4
2024-03-10 | Capricorn Star | Northern | Lizard Island | 0.75 | Strong wind and swell conditions | 3
2024-03-30 | Venus II | Northern | Boulder | 1 | Strong wind and swell conditions | 4
2024-03-31 | Venus II | Northern | Boulder | 1 | Strong wind and swell conditions | 4
2024-04-06 | Capricorn Star | Northern | Return to port | 1 | Injured crew drop off | 4
2024-04-07 | Capricorn Star | Northern | Return to port | 1 | Injured crew drop off | 4
2024-04-08 | Capricorn Star | Northern | Return to port | 1 | Injured crew drop off | 4
2024-04-14 | Tura | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2024-04-14 | Venus II | Northern | Fitzroy Island | 0.5 | Strong wind and swell conditions | 2
2024-04-16 | Tura | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2024-04-19 | Venus II | Northern | Moore 16-071 | 1 | Community engagement on pontoon | 4
2024-05-01 | Venus II | Northern | Rudder 16-023 | 0.5 | Strong wind and swell conditions | 2
2024-05-09 | Capricorn Star | Northern | Return to port | 0.5 | Mechanical issues | 2
2024-05-09 | Tura | Central | Backnumbers | 1 | Strong wind and swell conditions | 4
2024-05-10 | Capricorn Star | Northern | Normanby-Mabel | 0.25 | Strong wind and swell conditions | 1
2024-05-10 | Venus II | Northern | Cairns Port | 1 | Engagement with partners TSRA and GBRMPA | 4
2024-05-16 | Capricorn Star | Central | Backnumbers | 1 | Strong wind and swell conditions | 4
2024-05-18 | Capricorn Star | Northern | Wardle | 1 | Strong wind and swell conditions | 4
2024-05-19 | Capricorn Star | Northern | Wardle | 0.75 | Strong wind and swell conditions | 3
2024-05-20 | Capricorn Star | Northern | Wardle | 1 | Strong wind and swell conditions | 4
2024-05-23 | Tura | Central | Backnumbers | 1 | Strong wind and swell conditions | 4
2024-05-27 | Tura | Central | Kelso | 0.5 | Strong wind and swell conditions | 2
2024-05-27 | Venus II | Northern | Walker | 1 | Mechanical issues | 4
2024-05-28 | Tura | Northern | Yamacutta | 0.75 | Strong wind and swell conditions | 3
2024-05-30 | Capricorn Star | Northern | Batt 16-029 | 1 | Injured crew drop off | 4
2024-06-02 | Capricorn Star | Northern | Britomart | 0.5 | Strong wind and swell conditions | 2
2024-06-08 | Capricorn Star | Central | Trunk 18-027 | 0.5 | Mechanical issues | 2
2024-06-09 | Capricorn Star | Central | Trunk 18-027 | 0.5 | Mechanical issues | 2
2024-06-19 | Tura | Central | Barnett Patches | 0.5 | Sharks large aggressive behavoiur | 2
2024-06-25 | Tura | Northern | Round Russell | 0.25 | Mechanical issues | 1
2024-07-04 | Capricorn Star | Central | Reg Ward | 1 | Strong wind and swell conditions | 4
2024-07-05 | Capricorn Star | Central | Reg Ward | 1 | Strong wind and swell conditions | 4
2024-07-06 | Venus II | Northern | Irene | 1 | Strong wind and swell conditions | 4
2024-07-06 | Capricorn Star | Central | Kelso | 1 | Strong wind and swell conditions | 4
2024-07-07 | Venus II | Northern | Irene | 0.5 | Strong wind and swell conditions | 2
2024-07-07 | Capricorn Star | Central | Kelso | 1 | Strong wind and swell conditions | 4
2024-07-16 | Capricorn Star | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2024-07-17 | Capricorn Star | Central | Big Broadhurst No1 | 0.5 | Strong wind and swell conditions | 2
2024-07-18 | Capricorn Star | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2024-07-30 | Venus II | Northern | Irene | 1 | Strong wind and swell conditions | 4
2024-07-31 | Venus II | Northern | Irene | 0.5 | Strong wind and swell conditions | 2
2024-08-01 | Capricorn Star | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2024-08-02 | Capricorn Star | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2024-08-03 | Venus II | Northern | Irene | 0.25 | Strong wind and swell conditions | 1
2024-08-03 | Capricorn Star | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2024-08-04 | Capricorn Star | Central | Big Broadhurst No1 | 0.75 | Strong wind and swell conditions | 3
2024-08-07 | Capricorn Star | Central | Big Broadhurst No1 | 0.5 | Strong wind and swell conditions | 2
2024-08-08 | Capricorn Star | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2024-08-09 | Capricorn Star | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2024-08-10 | Capricorn Star | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2024-08-11 | Capricorn Star | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2024-08-12 | Capricorn Star | Central | Big Broadhurst No1 | 1 | Strong wind and swell conditions | 4
2024-08-23 | Venus II | Northern | Helsdon | 1 | Strong wind and swell conditions | 4
2024-09-04 | Capricorn Star | Central | Centipede | 1 | Strong wind and swell conditions | 4
2024-09-05 | Venus II | Northern | Mackay | 0.25 | Strong wind and swell conditions | 1
2024-09-05 | Capricorn Star | Central | Centipede | 1 | Strong wind and swell conditions | 4
2024-09-06 | Venus II | Northern | Evening 15-095 | 0.5 | Strong wind and swell conditions | 2
2024-09-07 | Capricorn Star | Central | Centipede | 1 | Strong wind and swell conditions | 4
2024-09-10 | Capricorn Star | Central | Kelso | 0.5 | Strong wind and swell conditions | 2
2024-09-12 | Venus II | Northern | Forrester | 1 | Strong wind and swell conditions | 4
2024-09-12 | Capricorn Star | Central | Wardle | 0.5 | Strong wind and swell conditions | 2
2024-09-14 | Capricorn Star | Central | Normanby-Mabel | 1 | Strong wind and swell conditions | 4
2024-09-15 | Capricorn Star | Central | Normanby-Mabel | 1 | Strong wind and swell conditions | 4
2024-10-02 | Capricorn Star | Northern | Eyrie 14-118 | 1 | Strong wind and swell conditions | 4
2024-10-03 | Capricorn Star | Northern | Helsdon | 1 | Strong wind and swell conditions | 4
2024-10-04 | Capricorn Star | Northern | Helsdon | 1 | Strong wind and swell conditions | 4
2024-10-27 | Capricorn Star | Northern | U/N 15-071c | 0.5 | Strong wind and swell conditions | 2
2024-11-12 | Capricorn Star | Northern | Return to Cairns port | 1 | Engagement with partners Sen Green | 4
2024-11-17 | Capricorn Star | Northern | Forrester | 1 | Strong wind and swell conditions | 4
2024-12-07 | Capricorn Star | Northern | Linnet | 0.5 | Strong wind and swell conditions | 2
2025-01-26 | Venus II | Northern | Batt 16-029 | 0.5 | Strong wind and swell conditions | 2
2025-01-26 | Capricorn Star | Northern | Batt 16-029 | 0.5 | Strong wind and swell conditions | 2
2025-02-08 | Capricorn Star | Northern | Return to Cairns port | 1 | Mechanical issues | 4
2025-02-11 | Venus II | Northern | Evening 15-095 | 1 | Strong wind and swell conditions | 4
2025-02-12 | Capricorn Star | Northern | U/N 15-071c | 0.5 | Strong wind and swell conditions | 2
2025-02-13 | Capricorn Star | Northern | U/N 15-071c | 0.75 | Strong wind and swell conditions | 3
2025-02-19 | Capricorn Star | Northern | Vicki Harriot | 0.75 | Strong wind and swell conditions | 3
2025-02-20 | Venus II | Northern | Irene | 1 | Strong wind and swell conditions | 4
2025-02-21 | Venus II | Northern | Evening 15-095 | 1 | Strong wind and swell conditions | 4
2025-02-21 | Capricorn Star | Northern | Batt 16-029 | 1 | Strong wind and swell conditions | 4
2025-02-22 | Venus II | Northern | Evening 15-095 | 0.75 | Strong wind and swell conditions | 3
2025-02-22 | Capricorn Star | Northern | Green Island | 1 | Strong wind and swell conditions | 4
2025-02-23 | Venus II | Northern | Batt 16-029 | 1 | Strong wind and swell conditions | 4
2025-03-07 | Venus II | Northern | Return to port | 0.5 | Picking up crew members | 2
2025-03-14 | Capricorn Star | Northern | Return to port | 1 | Picking up crew members | 4
2025-03-15 | Venus II | Northern | Linnet | 0.5 | Strong wind and swell conditions | 2
2025-03-15 | Capricorn Star | Northern | Batt 16-029 | 0.5 | Strong wind and swell conditions | 2
2025-03-16 | Capricorn Star | Northern | Batt 16-029 | 0.25 | Strong wind and swell conditions | 1
2025-03-17 | Venus II | Northern | Martin 14-123 | 0.5 | Strong wind and swell conditions | 2
2025-03-18 | Capricorn Star | Northern | Batt 16-029 | 0.5 | Strong wind and swell conditions | 2
2025-03-21 | Venus II | Northern | Return to port | 1 | Mechanical issues | 4
2025-03-21 | Capricorn Star | Northern | Return to Cairns port | 0.25 | Picking up crew members | 1
2025-03-22 | Venus II | Northern | Return to port | 1 | Mechanical issues | 4
2025-03-23 | Venus II | Northern | Return to port | 1 | Mechanical issues | 4